## Test cases Module 1
Module 1: Dummy Ticket
Test Case ID | Test Case Name | Description | Precondition | Test Steps | Test Date | Expected Result | Actual Result | Status | Remark
TC-DT-01 | Launch Homepage | Verify homepage loads and ticket form is visible | Browser open with stable internet | I open my browser and go to the ticket booking website https://onwardflightticket.com/ I check that the homepage loads properly and the booking form is visible. | 2025-08-31 | Homepage loads fully, ticket form visible | Homepage loaded in 2s, form visible | Pass | Works as expected
TC-DT-02 | Input Valid Details | Ensure valid details are accepted | User on homepage | I Select origin city and Select destination city then Pick valid travel date and then I Click "Find Flights!” | 2025-08-31 | 1.All fields accepted without error 2.flight details should display | Data accepted, no error triggered flight details displayed | Pass | Smooth input validation
TC-DT-03 | Submit With Missing Field | Check mandatory field validation | User on homepage | I have Leave "orgin"detail empty and Entered the "To" detail then I Entered "When" date and Click "Find Flights!” then I observe the error | 2025-08-31 | Validation error displayed for missing field " Please Enter the mandatory fields*" | Text “No Flights found” displayed | Fail | Error didn’t Shown in missed column
TC-DT-04 | Select the Flight | Ensure Flights found | Valid details filled | I have Filled all details and I have Clicked "Find Flights!” then Wait for system to processand Observe ticket preview then I have clicked on Select . | 2025-08-31 | First name , last Name , email column should be Displayed | First name , last Name , email column as been appeared | Pass | Flight selected successfully
TC-DT-05 | Checkout enables | Ensure valid details are accepted | User on checkout page | I have Enter First Name then I Entered last Name and clicked "Agree to Terms of Service" | 2025-08-31 | Checkout Button should enabled | Checkout Button has enabled | Pass | Checkout button successfully blue
TC-DT-06 | Submit With Missing Field in Checkout area | Check mandatory field validation | User on checkout page | I Leave First Name detail empty then I Enter Last name detail. I Enter Email Id & I Clicked "Agree to Terms of Service" | 2025-08-31 | Checkout Button must be Disabled | Checkout Button is disabled | Pass | Checkout button successfully not able to click
TC-DT-07 | Agree to Term of services check box functiona | Ensure to click on Agree to Term of services check box | Valid details filled | I Enter First Name detail and I Entered Last name detail I have Entered Email Id then didn’t Click on Agree to Term of services check box then I Clicked "Checkout" | 2025-08-31 | Confirm the error "Please tick this box if you want to proceed" | Error massage displayed | Pass | Works as expected
TC-DT-08 | Click Term of service | Ensure the Terms of Service link "https://onwardflightticket.com/terms " opens | Validate the Terms of Service | I Clicked on Term of Service | 2025-08-31 | Direct to the terms of service link and "Onward Flight Ticket" should appear | Directed to link and text appeared | Pass | Works as expected
TC-DT-09 | Ensure close button works | Ensure that we can close the selected flight details | User on checkout page | I Clicked on close button | 2025-08-31 | The selected flight details must been closed and list of flights details should appear | The selected flight detail as been closed and list of flights displayed | Pass | Works as expected
TC-DT-10 | cross-Browser Ticket Generation | Verify ticket generation works across different browsers | Browsers installed: Chrome, Firefox, Edge | I Open site in Chrome then Generated ticket with valid details I Repeated steps in Firefox then Repeated steps in Edge & Compare results across browsers | 2025-08-31 | Ticket generation and PDF download works consistently across all tested browsers | Ticket successfully generated and PDF downloaded in Chrome, Firefox, and Edge | Pass | Functionality consistent across browsers

## Test cases Module 2
Module 2: Payment
Test Case ID | Test Case Name | Description | Precondition | Test Steps | Test Date | Expected Result | Actual Result | Status | Remark
TC-PM-01 | Payment Page Load | Verify payment page loads properly | Ticket generated, user redirected to payment | I have Generated a ticket then I Clicked “Proceed to Payment” I Waited for page loaded and I Checked payment fields I Verified secure connection | 2025-09-01 | Payment page loads fully with card/payment fields visible | Page loads successfully | Pass | Works fine
TC-PM-02 | Valid Card Payment | Verify successful payment with valid card | Valid VISA/Mastercard test card | I have Entered valid card number I Entered expiry I Have Entered CVV then Clicked Pay then Observed confirmation | 2025-09-01 | Payment successful; confirmation shown | Payment accepted, confirmation displayed | Pass | Smooth flow
TC-PM-03 | Invalid Card Number | Verify error on invalid card | Payment page open | I have Ented invalid card digits I have Ented expiry & CVV then Clicked Pay then Waited for response And I Observed error | 2025-09-01 | Error message “Invalid card number” | Error message displayed correctly | Pass | Validation works
TC-PM-04 | Expired Card | Verify error for expired card date | Payment page open | I Entered valid card number and Entered expired date and I Entered CVV then Clicked Pay then Observed response | 2025-09-01 | Error message shown | “Card expired” message displayed | Pass | Validation correct
TC-PM-05 | Missing Field | Verify error when mandatory fields are blank | Payment page open | I have Leaved card number blank then I Entered other details I Clicked Pay and Waited for response I Observeed error. | 2025-09-01 | Error shown for blank fields | “Card number required” displayed | Pass | Correct handling
TC-PM-06 | Payment Confirmation Email | Verify confirmation email is sent | Valid payment processed | I have Completed valid payment and I Opened registered email inbox I have Located email then Opened email it then Verified content | 2025-09-01 | Email received with ticket/payment details | No email received | Fail | Defect in email trigger
TC-PM-07 | Duplicate Payment Prevention | Ensure duplicate charges not allowed | Valid payment completed once | I Pay for ticket and I Clicked back & try paying again then Submitted payment I Observed response then Checked bank statement | 2025-09-01 | Second attempt blocked; no double charge | Second attempt processed & charged | Fail | Critical financial defect
TC-PM-08 | Payment Timeout Handling | Verify system handles timeout gracefully | Payment gateway active | I Opened payment page then I Waitted idle >10 mins I Resumed & paid I have Observed system response and I Checked error | 2025-09-01 | Session expired message shown | Payment session timed out without warning | Fail | Poor handling
TC-PM-09 | Currency Display | Verify currency shown as USD $5 | Payment page open | I have Navigated to payment page I have Observed price field then I Verified currency symbol I have Cross-check against site pricing Then I Confirmed consistency | 2025-09-01 | Price displayed in USD with correct amount | Price shown as $5 correctly | Pass | Matches requirement

## Bug Report Module 1 & 2
Module 1: Dummy Ticket
Bug ID | Title | Test Case ID | Description | Precondition | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Reporter | Date Reported | Status | Remark
BUG-DT-01 | Missing validation error in Find Flights | TC-DT-03 | Validation error not triggered when mandatory field is left blank. Instead, system shows “No Flights Found.” | User on homepage | 1. Open homepage 2. Leave “From” city blank 3. Enter “To” city 4. Click “Find Flights” | Validation error for missing field should be displayed " Please Enter the mandatory fields*" | “No Flights Found” message displayed | High | High | Suwathi | 2025-09-01 | Open | validation bug, impacts user flow
Module 2: Payment
Bug ID | Title | Test Case ID | Description | Precondition | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Reporter | Date Reported | Status | Remark
BUG-PM-01 | Confirmation Email Not Sent | TC-PM-06 | No confirmation email after successful payment | Valid payment processed | 1. Complete payment 2. Check inbox | Confirmation email received | No email received | High | High | Suwathi | 2025-09-02 | Open | Impacts user trust
BUG-PM-02 | Duplicate Payment Allowed | TC-PM-07 | System allows duplicate charges | One successful payment done | 1. Pay once 2. Repeat payment | System should block duplicate | Duplicate charge processed | Critical | High | Suwathi | 1900-01-01 | Open | Financial risk
BUG-PM-03 | Session Timeout Not Handled | TC-PM-08 | No warning/error when payment session expires | Idle on payment page | 1. Stay idle >10 mins 2. Pay | “Session expired” error expected | Payment failed silently | Medium | Medium | Suwathi | 2025-09-02 | Open | Usability issue

## Test Scenario Module 1& 2
Module 1: Dummy Ticket Generation
Test Case ID | Scenario | Description | Precondition | Test Steps | Test Data | Post Condition | Expected Result | Module | Priority | Test Type
TC-DT-01 | Homepage Load | Verify homepage loads and ticket form is visible | Browser open with internet | I open my browser and go to the ticket booking website https://onwardflightticket.com/ I check that the homepage loads properly and the booking form is visible. | N/A | Homepage loaded, user can start booking | Homepage loads in <3s, booking form visible | Dummy Ticket | High | Functional
TC-DT-02 | Input Valid Details | Ensure valid details are accepted | User on homepage | I Select origin city and Select destination city then Pick valid travel date and then I Click "Find Flights!” | Origin: Chennai Destination: Delhi Date: 05-Sep-2025 | List of available flights shown | Flights displayed | Dummy Ticket | High | Functional
TC-DT-03 | Missing Mandatory Fields | Validation for missing input | User on homepage | I have Leave "orgin"detail empty and Entered the "To" detail then I Entered "When" date and Click "Find Flights!” then I observe the error | From: [blank] To: Delhi Date: 06-Sep-2025 | Error message displayed; user remains on homepage | Validation error → "Please Enter the mandatory fields*" | Dummy Ticket | High | Functional
TC-DT-04 | Select Flight | Verify flight selection works | Flight results available | I have Filled all details and I have Clicked "Find Flights!” then Wait for system to processand Observe ticket preview then I have clicked on Select . | From: Chennai To: Delhi Date: 07-Sep-2025 | User redirected to passenger details page | Checkout form appears with Name, Email fields | Dummy Ticket | Medium | Functional
TC-DT-05 | Checkout Enable | Verify checkout button activates | On checkout page | I have Enter First Name then I Entered last Name and clicked "Agree to Terms of Service" | First Name: Suwathi Last Name: Karthikeyan | Checkout option ready for next step | Checkout button enabled | Dummy Ticket | Medium | Functional
TC-DT-06 | Checkout Missing Field | Verify checkout blocked if field empty | On checkout page | I Leave First Name detail empty then I Enter Last name detail. I Enter Email Id & I Clicked "Agree to Terms of Service" | First Name: [blank] Last Name: Karthikeyan Email: test@mail.com | User cannot continue without mandatory fields | Checkout disabled | Dummy Ticket | High | Functional
TC-DT-07 | T&C Validation | Verify T&C checkbox mandatory | On checkout page | I Enter First Name detail and I Entered Last name detail I have Entered Email Id then didn’t Click on Agree to Term of services check box then I Clicked "Checkout" | First Name: Suwathi Last Name: Karthikeyan Email: ravi@test.com | User forced to tick T&C before continuing | Error: "Please tick this box if you want to proceed" | Dummy Ticket | High | Functional
TC-DT-08 | Terms of Service Link | Verify TOS opens | Checkout page visible | I Clicked on Term of Service | N/A | User navigated to Terms page in new tab | Redirect to TOS page | Dummy Ticket | Medium | Non-Functional
TC-DT-09 | Close Flight Selection | Verify closing flight selection | Flight selected | I Clicked on close button | N/A | User returns to flight list | Flight selection closed, results shown | Dummy Ticket | Low | Functional
TC-DT-10 | Cross-Browser Ticket | Verify ticket generation across browsers | Browsers installed | I Open site in Chrome then Generated ticket with valid details I Repeated steps in Firefox then Repeated steps in Edge & Compare results across browsers | Valid passenger details | Ticket + PDF download consistent | Ticket generated consistently in all browsers | Dummy Ticket | High | Non-Functional
Module 2: Payment
Test Case ID | Scenario | Description | Precondition | Test Steps | Test Data | Post Condition | Expected Result | Module | Priority | Test Type
TC-PM-01 | Payment Page Load | Verify payment page loads | Ticket booked, redirect to payment | I have Generated a ticket then I Clicked “Proceed to Payment” I Waited for page loaded and I Checked payment fields I Verified secure connection | N/A | User can view secure fields | Payment page loads securely | Payment | High | Non-Functional
TC-PM-02 | Valid Card Payment | Verify success with valid card | On payment page | I have Entered valid card number I Entered expiry I Have Entered CVV then Clicked Pay then Observed confirmation | Card: 4111 1111 1111 1111 Exp: 12/26 CVV: 123 | User redirected to confirmation, ticket booked | Payment successful, confirmation shown | Payment | High | Functional
TC-PM-03 | Invalid Card | Verify invalid card rejected | On payment page | I have Ented invalid card digits I have Ented expiry & CVV then Clicked Pay then Waited for response And I Observed error | Card: 1234 5678 9876 5432 | User cannot proceed with invalid card | Error: “Invalid card number” | Payment | High | Functional
TC-PM-04 | Expired Card | Verify expired date rejected | On payment page | I Entered valid card number and Entered expired date and I Entered CVV then Clicked Pay then Observed response | Card: 4111 1111 1111 1111 Exp: 01/23 | User blocked from payment | Error: “Card expired” | Payment | High | Functional
TC-PM-05 | Missing Fields | Verify mandatory fields required | On payment page | I have Leaved card number blank then I Entered other details I Clicked Pay and Waited for response I Observeed error. | Card: [blank] | User cannot pay until all details filled | Error: “Card number required” | Payment | High | Functional
TC-PM-06 | Payment Confirmation Email | Verify email sent after payment | Payment successful | I have Completed valid payment and I Opened registered email inbox I have Located email then Opened email it then Verified content | Email: test@mail.com | User gets e-ticket in inbox | Email received with ticket/payment details | Payment | High | Functional
TC-PM-07 | Duplicate Payment | Prevent duplicate charges | Valid payment already done | I Pay for ticket and I Clicked back & try paying again then Submitted payment I Observed response then Checked bank statement | Card: 4111 1111 1111 1111 | User not charged twice | Second payment blocked | Payment | ⚠️ Critical | Functional
TC-PM-08 | Timeout Handling | Verify timeout behavior | On payment page | I Opened payment page then I Waitted idle >10 mins I Resumed & paid I have Observed system response and I Checked error | Card: 4111 1111 1111 1111 | User prompted to restart payment | Session expired error | Payment | Medium | Non-Functional
TC-PM-09 | Currency Display | Verify correct currency shown | Payment page open | I have Navigated to payment page I have Observed price field then I Verified currency symbol I have Cross-check against site pricing Then I Confirmed consistency | Price: $5 | User sees consistent pricing | Correct USD $5 displayed | Payment | Low | Functional

## Test Plan Module 1 & 2
Test Plan – Dummy Ticket Generation & Payment Modules
Section | Details
Test Plan ID | TP-DTG-PM-2025-01
Application Under Test (AUT) | Onward Flight Ticket (Dummy Ticket Generation & Payment System)
Prepared By | Suwathi
Date | 2025-08-31
Version | v1.0
References | Business Requirement Doc, v1.2, Design Docs, Dummy Payment Gateway Specs
Objectives & Scope
In Scope | Out of Scope
✅ Ticket booking flow (search, select, checkout) | ❌ Real payment processing
✅ Ticket download (PDF) | ❌ Mobile application testing
✅ Payment flow with dummy cards | ❌ Backend airline database integration
✅ Mandatory field validations | ❌ Performance load beyond 50 concurrent users
✅ Cross-browser validation (Chrome, Firefox, Edge)
Features to be Tested
Module | Features Covered
Dummy Ticket | Homepage load, input validation, flight search, select flight, checkout enable/disable, Terms & Conditions validation, ticket generation & cross-browser support
Payment | Payment page load, valid/invalid card validation, expired card handling, mandatory field validation, duplicate payment prevention, timeout handling, email confirmation, currency display
Entry & Exit Criteria
Entry Criteria | Exit Criteria
Test environment set up | All planned test cases executed
Dummy data (names, emails, card numbers) available | Critical & high severity bugs fixed & retested
AUT deployed in QA server | Test Summary Report submitted
UAT sign-off received
Responsibilities
Role | Responsibility
QA Engineer (Suwathi) | Test design, execution, bug reporting, documentation
Developer (Gokila) | Fixing reported defects
QA Lead (Velam) | Test plan approval, prioritization, sign-off
Project Manager (Kamali) | Timeline & delivery ownership
Test Environment
Component | Details
OS | Windows 11 Pro
Browsers | Chrome v118, Firefox v117, Edge v112
Test Tools | Excel (Test Cases), JIRA (Defect Tracking), Email server simulator
Test Data | Dummy names, valid & invalid card numbers (VISA, MasterCard)
Test Data Requirements
Data Type | Example Values
Names | John Doe, Priya Sharma
Email | test.user@mail.com
Cards | Valid VISA: 4111 1111 1111 1111 Invalid: 1234 5678 9012 3456 Expired: 01/23
Travel Dates | Current & future valid dates
Risks & preventions
Risk | Mitigation
Validation errors not triggered correctly | Add negative test coverage
Payment confirmation email not received | Raise as High priority defect, verify mail server logs
Duplicate payments processed | Add stricter duplicate transaction handling test cases
Schedule & Timeline
Activity | Timeline
Test Design | 29–30 Aug 2025
Test Execution | 31 Aug – 02 Sept 2025
Bug Fix & Retest | 03–04 Sept 2025
Test Closure | 2025-09-05
Requirements Traceability Matrix
Module 1: Dummy Ticket Generation
Scenario ID | Scenario Description | Mapped Test Cases | Priority | Status
SCN-DT-01 | Homepage loads with ticket form | TC-DT-01 | High | ✅ Pass
SCN-DT-02 | Valid details search flights | TC-DT-02 | High | ✅ Pass
SCN-DT-03 | Missing mandatory fields show validation | TC-DT-03 | High | ❌ Fail
SCN-DT-04 | Select flight & view checkout | TC-DT-04 | High | ✅ Pass
SCN-DT-05 | Checkout validation & T&C handling | TC-DT-05, TC-DT-06, TC-DT-07 | Medium | ✅ Pass
SCN-DT-06 | Terms of Service & close functionality | TC-DT-08, TC-DT-09 | Low | ✅ Pass
SCN-DT-07 | Ticket generation & download works across browsers | TC-DT-10 | High | ✅ Pass
Module 2: Payment
Scenario ID | Scenario Description | Mapped Test Cases | Priority | Status
SCN-PM-01 | Payment page load & secure connection | TC-PM-01 | High | ✅ Pass
SCN-PM-02 | Successful valid card payment | TC-PM-02 | High | ✅ Pass
SCN-PM-03 | Invalid/expired card validation | TC-PM-03, TC-PM-04 | High | ✅ Pass
SCN-PM-04 | Mandatory field validation | TC-PM-05 | High | ✅ Pass
SCN-PM-05 | Payment confirmation email | TC-PM-06 | High | ❌ Fail
SCN-PM-06 | Duplicate payment prevention | TC-PM-07 | ⚠️ Critical | ❌ Fail
SCN-PM-07 | Timeout handling | TC-PM-08 | ⚠️ Critical | ❌ Fail
SCN-PM-08 | Currency display consistency | TC-PM-09 | Medium | ✅ Pass
Deliverables
Document | Owner
Test Plan | QA Engineer (Suwathi)
Test Scenarios & Cases | QA Engineer (Suwathi)
Defect Reports | QA Engineer (Suwathi)
Test Summary Report | QA Lead (Velam)
Approval
Name | Role | Signature | Date
QA Lead (Velam) | Test Plan Approval |  | 2025-09-05
Project Manager (Kamali) | Final Approval |  | 2025-09-05

## Defect Life Cycle
Defect Life Cycle for Module 1 & 2
Bug ID | Module | Defect Title | Current Stage | Description | Postcondition | Date Reported | Reported By | Assigned To | Responsible Role | Severity / Priority
BUG-DT-01 | Dummy Ticket Generation | Missing validation error in “Find Flights” field | New → Assigned | Validation error not triggered when From field left blank; shows “No Flights”. | User prevented from booking with incomplete data | 2025-09-01 | Suwathi | – (Unassigned) | Tester → Developer | High / High
BUG-PM-06 | Payment | Payment confirmation email not received | Reopened | Payment goes through but no email is triggered. | User must receive ticket email confirmation | 2025-09-01 | Suwathi | Dev1 | Developer → Tester | High / Medium
BUG-PM-07 | Payment | Duplicate payment allowed | Open | User able to make duplicate charge by going back and resubmitting. | Only one valid charge should be processed | 2025-09-01 | Suwathi | Dev2 | Developer | Critical / High
BUG-PM-08 | Payment | Payment timeout not handled gracefully | New | Session expires without warning; user loses progress. | User notified of timeout and allowed to retry | 2025-09-01 | Suwathi | Dev3 | Tester → Lead → Dev | Medium / Medium
Colour code reference in Defect life cycle
Status / Stage | Color Code | Meaning / Description
New | Blue | Defect is newly reported, not yet assigned.
Assigned | Yellow | Defect has been assigned to developer for fixing.
Open / In Progress | Orange | Developer is actively working on the defect.
Fixed | Light Green | Developer has fixed the defect, pending retest.
Retest | Purple | Tester is re-executing to verify the fix.
Verified / Closed | Dark Green | Defect has been validated and closed.
Reopened | Red | Defect fix failed, bug is reopened.
Deferred | Gray | Defect resolution postponed to future release.
Rejected | Black | Defect not valid / will not be fixed.

## Test Execution and Report
Test Execution for Module 1: Dummy Ticket Generation
Execution Summary
Total Test Cases | Executed | Passed | Failed | Blocked/NA | Pass %
10 | 10 | 8 | 2 | 0 | 80%
Detailed Execution Report
Test Case ID | Scenario | Execution Date | Status | Defect ID (if Fail) | Remarks
TC-DT-01 | Launch Homepage | 2025-08-31 | Pass | – | Loaded successfully
TC-DT-02 | Input Valid Details | 2025-08-31 | Pass | – | Flight displayed
TC-DT-03 | Submit with Missing Field | 2025-08-31 | Fail | BUG-DT-01 | Validation missing
TC-DT-04 | Select the Flight | 2025-08-31 | Pass | – | Works fine
TC-DT-05 | Checkout enables | 2025-08-31 | Pass | – | Button enabled
TC-DT-06 | Missing Field in Checkout | 2025-08-31 | Pass | – | Validation handled
TC-DT-07 | Agree To Terms Checkbox | 2025-08-31 | Pass | – | Error displayed
TC-DT-08 | Click Terms of Service Link | 2025-08-31 | Pass | – | Link opened
TC-DT-09 | Close Button Functionality | 2025-08-31 | Pass | – | Flights displayed
TC-DT-10 | Cross-Browser Ticket Generation | 2025-08-31 | Pass | – | All browsers worked
Test Execution for Module 2: Payment
Execution Summary
Total Test Cases | Executed | Passed | Failed | Blocked/NA | Pass %
9 | 9 | 6 | 3 | 0 | 66.7%
Detailed Execution Report
Test Case ID | Scenario | Execution Date | Status | Defect ID (if Fail) | Remarks
TC-PM-01 | Payment Page Load | 2025-09-01 | Pass | – | Page loaded correctly
TC-PM-02 | Valid Card Payment | 2025-09-01 | Pass | – | Payment successful
TC-PM-03 | Invalid Card Number | 2025-09-01 | Pass | – | Error displayed
TC-PM-04 | Expired Card | 2025-09-01 | Pass | – | Error shown
TC-PM-05 | Missing Field | 2025-09-01 | Pass | – | Validation works
TC-PM-06 | Payment Confirmation Email | 2025-09-01 | Fail | BUG-PM-06 | Email not sent
TC-PM-07 | Duplicate Payment Prevention | 2025-09-01 | Fail | BUG-PM-07 | Double charge issue
TC-PM-08 | Payment Timeout Handling | 2025-09-01 | Fail | BUG-PM-08 | Timeout not handled
TC-PM-09 | Currency Display | 2025-09-01 | Pass | – | USD $5 shown
Observations
* Dummy Ticket Generation module is largely stable (80% pass rate).
* Payment Module has critical blocking defects (financial issues: duplicate charge, missing email, poor timeout handling).
* Release Recommendation: Not ready for production until High severity defects are resolved.